## How to Use
Decipher PMO — Project Workbook
Live tabs for tracking a single project end to end. Blue = inputs you change. Other cells calculate.
Tab | What it tracks
Identification | Project name, sponsor, TPM, dates, current RAG
Charter | Authorization summary — objectives, scope, budget
RACI | Decision/deliverable accountability (one A per row)
WBS & Estimates | Scope decomposition + three-point (PERT) estimates
Schedule | Milestones: baseline vs forecast, variance, RAG
Budget & EVM | Earned value: PV/EV/AC and CPI/SPI/EAC
Risk Register | Scored risks: inherent vs residual, response, owner
RAID | Risks/Assumptions/Issues/Dependencies running log
RTM | Requirement -> design -> test traceability + coverage
Dependencies | Cross-team dependencies and float
Decisions & Changes | Decision log + change register
Change Requests | Formal change control / CCB
UAT Log | Test case execution and pass rate
Escalation Log | Tiered escalations and resolution
Status | Weekly RAG rollup
Lessons | Lessons learned register

## Glossary
Glossary — acronyms used in this workbook
Every abbreviation used in the tabs, written out.
Acronym | Full term
PMO | Project / Program Management Office
PM | Project Manager
PgM | Program Manager
TPM | Technical Program Manager
SRO | Senior Responsible Owner
BAU | Business as Usual (steady-state operations)
RAG | Red / Amber / Green status rating
RAID | Risks, Assumptions, Issues, Dependencies
RACI | Responsible, Accountable, Consulted, Informed
CCB | Change Control Board
CR | Change Request
ECD | Estimated Completion Date
KPI | Key Performance Indicator
OKR | Objectives and Key Results
EVM | Earned Value Management
PV | Planned Value
EV | Earned Value
AC | Actual Cost
CV | Cost Variance (EV minus AC)
SV | Schedule Variance (EV minus PV)
CPI | Cost Performance Index (EV divided by AC)
SPI | Schedule Performance Index (EV divided by PV)
BAC | Budget at Completion
EAC | Estimate at Completion (forecast final cost)
ETC | Estimate to Complete
VAC | Variance at Completion
WBS | Work Breakdown Structure
PERT | Program Evaluation and Review Technique
P x I | Probability x Impact (risk score)
RTM | Requirements Traceability Matrix
UAT | User Acceptance Testing
DoR | Definition of Ready
DoD | Definition of Done
SOW | Statement of Work
RFP | Request for Proposal
SLA | Service Level Agreement
OCM | Organizational Change Management
FTE | Full-Time Equivalent (one full-time person)
NPV | Net Present Value
IRR | Internal Rate of Return
ROI | Return on Investment
GRC | Governance, Risk, and Compliance
IAM | Identity and Access Management
ZTNA | Zero Trust Network Access
PAM | Privileged Access Management
SIEM | Security Information and Event Management
MFA | Multi-Factor Authentication
IdP | Identity Provider
VPN | Virtual Private Network
PCI-DSS | Payment Card Industry Data Security Standard
ISO | International Organization for Standardization
NIST | National Institute of Standards and Technology

## Identification
Project Identification
Field | Value
Project name | Project Atlas — ZTNA + PAM
Sponsor | CISO, Bristol Financial
TPM | (name)
Start date | 2026-01-12
Target end | 2026-09-30
Budget at completion (BAC) | 2400000
Current phase | Execute
Overall RAG | Amber

## Charter
Charter — Summary
Item | Detail
Problem / opportunity | 14 legacy access paths; 3 audit findings; rising breach exposure
Objective 1 | Reduce standing privileged access by 80% by go-live
Objective 2 | Conditional access on 100% of in-scope apps
In scope | ZTNA rollout (3 waves); PAM for privileged accounts
Out of scope | Legacy firewall decommission (Phase 2)
Contingency reserve ($) | 288000
Sponsor sign-off date | 2026-01-10

## RACI
RACI Matrix (Responsible, Accountable, Consulted, Informed)
Use exactly one A per row.
Activity / Decision | Sponsor | TPM | Eng Lead | Security | Business Owner | One-A check
Approve charter | A | R | C | C | C | OK
Go/no-go cutover | A | R | C | C | C | OK
Approve change request | A | R | C | C | C | OK
Risk acceptance | A | C | C | R | C | OK
UAT sign-off | C | R | C | C | A | OK

## WBS & Estimates
Work Breakdown Structure (WBS) & Three-Point Estimates
PERT expected = (O + 4M + P)/6
WBS ID | Work package | Owner | Optimistic (d) | Most likely (d) | Pessimistic (d) | PERT expected (d) | Std dev
1.1 | ZTNA discovery | Sec Eng | 8 | 12 | 20 | 12.6667 | 2
1.2 | Policy engine design | Architect | 10 | 15 | 25 | 15.8333 | 2.5
1.3 | Build & integrate | Eng | 18 | 28 | 45 | 29.1667 | 4.5
1.4 | UAT & cutover | TPM | 6 | 10 | 18 | 10.6667 | 2
2.1 | PAM discovery | Sec Eng | 6 | 12 | 20 | 12.3333 | 2.3333
2.2 | PAM build | Eng | 15 | 22 | 35 | 23 | 3.3333
| Total expected effort (d) |  |  |  |  | 103.6667

## Schedule
Schedule & Milestones
Variance = forecast - baseline (days). RAG auto.
Milestone | Baseline date | Forecast date | Variance (days) | Status | RAG
Discovery complete | 2026-02-13 | 2026-02-13 | 0 |  | Green
Pilot go-live | 2026-04-10 | 2026-04-17 | 7 |  | Amber
Wave 1 cutover | 2026-05-29 | 2026-06-12 | 14 |  | Amber
UAT exit | 2026-07-10 | 2026-07-10 | 0 |  | Green
Program close | 2026-09-30 | 2026-10-09 | 9 |  | Amber

## Budget & EVM
Budget & Earned Value (EVM)
EVM = Earned Value Management. CPI = Cost Performance Index (EV/AC); SPI = Schedule Performance Index (EV/PV); EAC = Estimate at Completion (BAC/CPI). Blue = inputs.
BAC ($) | 2400000
Period | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | CV | SV | CPI | SPI
Wk 4 | 300000 | 290000 | 310000 | -20000 | -10000 | 0.93548 | 0.96667
Wk 8 | 640000 | 600000 | 650000 | -50000 | -40000 | 0.92308 | 0.9375
Wk 13 | 1100000 | 950000 | 1080000 | -130000 | -150000 | 0.87963 | 0.86364
EAC (BAC/CPI) | 2728421.0526
VAC (BAC-EAC) | -328421.0526

## Time & Cost
Resource Tracking — Time & Cost
Actual hours and cost by person (employees & contractors). Cost = rate x hours. Burn = cost / budget. Blue = inputs.
Name | Type | Role | Bill rate ($/hr) | Hours (period) | Cost (period) | Cum. hours | Budget hours | Budget cost ($) | Burn % | PO / Invoice ref | Status
M. Vasquez | Employee | ZTNA lead | 0 | 32 | 0 | 210 | 520 | 0 | 0% | - | On plan
T. Adebayo | Employee | PAM lead | 0 | 30 | 0 | 180 | 520 | 0 | 0% | - | On plan
A. Okafor | Contractor | Identity engineer | 145 | 38 | 5510 | 360 | 640 | 92800 | 56.25% | PO-2231 / INV-014 | Active
L. Chen | Contractor | Pen tester (Ph3) | 160 | 12 | 1920 | 12 | 160 | 25600 | 7.5% | PO-2240 / - | Mobilizing
Total |  |  |  |  | 7430 |  |  | 118400
Note: contractor cost (period) feeds Budget & EVM Actual Cost (AC). Reconcile PO/invoice monthly.

## Risk Register
Risk Register & Response
Score = Probability x Impact (P x I, 1-5 each). Residual after response.
ID | Risk (if/then) | Category | P | I | Inherent | Response | Owner | Res P | Res I | Residual | Status
R-01 | If PAM onboarding slips, UAT delayed | Vendor | 4 | 4 | 16 | Mitigate: weekly checkpoint + credit | TPM | 2 | 4 | 8 | Mitigating
R-02 | If policy engine cannot enforce legacy rules, access lost | Technical | 3 | 5 | 15 | Mitigate: fallback VPN 30d | Eng Lead | 2 | 3 | 6 | Mitigating
R-03 | If EMEA testers unavailable, sign-off slips | Org | 3 | 3 | 9 | Sponsor ask for named testers | OCM | 2 | 2 | 4 | Open
R-04 | Holiday freeze compresses cutover | Schedule | 5 | 2 | 10 | Accept; 5d reserve | TPM | 5 | 2 | 10 | Accepted
| Total residual exposure | [8 empty] | 28

## RAID
RAID Log (Risks, Assumptions, Issues, Dependencies)
ID | Type | Description | P x I / Urgency | Owner | Due | Status
A1 | Assumption | Directory sync ready by Feb | - | Eng | 2026-02-01 | Open
I1 | Issue | Test data masking incomplete | High | QA | 2026-03-10 | Open
D1 | Dependency | IdP federation from Platform team | - | Platform | 2026-02-20 | At risk

## RTM
Requirements Traceability
Requirements Traceability Matrix (RTM). Coverage = % of requirements with a passing test.
Req ID | Requirement | Priority | Design ref | Build item | Test case | Result | Accepted?
BRD-014 | Conditional access by device posture | Must | PE 4.2 | PE-217 | TC-031 | Pass | Yes
BRD-022 | Self-service access request | Should | Portal PRD | PORTAL-88 | TC-050 | Fail | Conditional
BRD-031 | Custom block-page branding | Could | - | - | - | Deferred | No
| Pass coverage (all reqs) |  |  |  |  | 33.33%

## Dependencies
Cross-Team Dependencies
ID | Provider team | Receiver | Deliverable | Needed by | Status | Float (days)
DEP-1 | Platform/IdP | ZTNA | SAML federation | 2026-02-20 | At risk | -3
DEP-2 | Network | ZTNA | Firewall rule changes | 2026-03-05 | On track | 6
DEP-3 | Vendor (BeyondTrust) | PAM | Vault deployment | 2026-03-15 | On track | 4

## Decisions & Changes
Decisions & Changes Log
ID | Type | Decision / change | Rationale | Authority | Date | Status
D-12 | Decision | Retain VPN path 30 days post-cutover | Mitigate R-02 | SteerCo | 2026-04-02 | Closed
C-07 | Change | Defer biometric auth to Phase 2 | Enrollment infra not ready | Sponsor | 2026-04-18 | Approved

## Change Requests
Change Control (CCB)
Formal change control. CCB = Change Control Board. Impact assessed before approval.
CR ID | Description | Scope impact | Schedule (d) | Cost ($) | Risk impact | Recommendation | CCB decision
CR-09 | Add custom block-page branding | +1 feature | 5 | 18000 | Low | Defer to Wave 2 | Deferred
CR-11 | Add 2 EMEA test environments | Test scope | 3 | 22000 | Reduces UAT risk | Approve | Approved

## UAT Log
User Acceptance Testing (UAT) — Test Case Log
Pass rate auto-calculated.
Test ID | Scenario | Severity if fail | Result | Defect ID
TC-031 | Finance managed device reaches payroll <2s | S2 | Pass
TC-032 | Unmanaged device blocked w/ message | S1 | Pass
TC-050 | Self-service reset end-to-end | S3 | Fail | DEF-22
TC-051 | Break-glass access logged | S1 | Pass
| Pass rate |  | 75%

## Escalation Log
Escalation Log
ID | Tier | Issue | Raised | Owner | SLA (h) | Resolved | Outcome
E-1 | Tier 2 (Sponsor) | PAM vendor slip > buffer | 2026-04-30 | TPM | 48 | 2026-05-02 | Credit invoked; weekly checkpoint

## Status
Weekly Status Rollup
RAG thresholds objective (see Schedule/EVM).
Week | Scope RAG | Schedule RAG | Cost RAG | Overall | Top risk | Next milestone
Wk 13 | Green | Amber | Amber | Amber | R-01 PAM slip | Wave 1 cutover

## Lessons
Lessons Learned Register
ID | What happened | Root cause | Recommendation | Owner | Status
L-1 | Directory-sync lead time underestimated | Optimistic vendor estimate | Add 2-wk buffer for IdP deps | TPM | Open
L-2 | Legacy-app rules needed dedicated DoD | Coverage gap in quality plan | Add legacy-app DoD checklist | QA | Adopted