## How to Use
Decipher PMO — Program Workbook
Live tabs for multi-component program tracking. Blue = inputs.
Tab | What it tracks
Identification | Program name, sponsor, dates, overall RAG
Roadmap | Tranches and milestones over time
Components | Constituent projects, status, % complete rollup
Tranche Plan | Tranche outcomes + end-of-tranche go/no-go
Program RAID | Cross-component risks/assumptions/issues/deps
Program Risk | Aggregated and systemic risk + exposure
Dependencies | Cross-component dependencies
Capacity & Demand | Supply vs demand by skill
Decisions & Changes | Program-level decisions and changes
Benefits | Benefits realization: planned vs realized
Program Budget | Funding and spend across components
Closure | Program closure checklist

## Identification
Program Identification
Field | Value
Program name | Bristol Identity & Access Program
SRO / Sponsor | CISO
Program manager | (name)
Start | 2026-01-01
Target close | 2027-03-31
Total funding ($) | 6400000
Overall RAG | Amber

## Roadmap
Program Roadmap
Tranches across the program timeline.
Tranche | Window | Target capability / outcome | Key milestone | Status
T1 Foundations | Q1-Q2 2026 | Identity baseline + ZTNA pilot | Pilot go-live | In progress
T2 Rollout | Q3 2026 | ZTNA org-wide + PAM live | Wave 3 cutover | Planned
T3 Optimize | Q4 2026-Q1 2027 | Decommission legacy; SIEM uplift | Legacy off | Planned

## Components
Component Initiatives
% complete rolls up to program.
Component | Lead | Phase | RAG | % complete | Budget ($) | Spent ($)
ZTNA rollout | TPM A | Execute | Amber | 55 | 2400000 | 1080000
PAM implementation | TPM B | Build | Green | 40 | 900000 | 360000
SIEM uplift | TPM C | Plan | Green | 10 | 1200000 | 90000
Program |  |  |  | 35 | 4500000 | 1530000

## Tranche Plan
Tranche Plan & End-of-Tranche Review
Tranche | Outcomes | Benefits expected | End-of-tranche review date | Go/No-Go | Notes
T1 | Identity baseline, ZTNA pilot | Audit finding 1 closed | 2026-06-30 | Go | Pilot stable
T2 | Org-wide ZTNA + PAM | Standing privileged access -80% | 2026-09-30 | Pending

## Program RAID
Program-Level RAID
Only cross-component items.
ID | Type | Description | Severity | Owner | Status
PR-1 | Risk | Shared identity team over-allocated across ZTNA+PAM | High | PgM | Mitigating
PD-1 | Dependency | SIEM uplift depends on ZTNA log schema | Medium | TPM C | Open

## Program Risk
Program Risk (Aggregated)
Score = P x I. Systemic/cross-component.
ID | Program risk | Source | P | I | Exposure | Response | Owner | Status
PRISK-1 | Identity-skill bottleneck across components | Aggregated | 4 | 4 | 16 | Contract specialist; re-sequence | PgM | Mitigating
PRISK-2 | Benefit shortfall if adoption < 80% | Strategic | 3 | 4 | 12 | OCM reinforcement plan | Bus Owner | Open
| Total program exposure |  |  |  | 28

## Dependencies
Cross-Component Dependencies
ID | From component | To component | Deliverable | Needed by | Status
XD-1 | ZTNA | SIEM uplift | Log schema + feeds | 2026-08-01 | Open
XD-2 | PAM | ZTNA | Privileged account inventory | 2026-03-15 | On track

## Capacity & Demand
Capacity & Demand
Gap = demand - supply (FTE).
Skill / team | Supply (FTE) | Demand (FTE) | Gap | Flag
Identity specialists | 2 | 3.2 | 1.2 | SHORT
Security engineering | 6 | 5 | -1 | ok
OCM | 1.5 | 1.8 | 0.3 | SHORT

## Decisions & Changes
Program Decisions & Changes
ID | Type | Decision / change | Authority | Date | Status
PD-3 | Decision | Defer SIEM uplift to H2 (capacity) | Program Board | 2026-04-15 | Closed

## Benefits
Benefits Realization
% realized = realized / target.
Benefit | Owner (BAU) | Baseline | Target | Realized to date | % realized
Standing privileged access reduction | Head of IT Ops | 100% | -80% | -52%
Access-related incidents / yr | CISO | 46 | 18 | 29 | 60.71%

## Program Budget
Program Budget
Variance = funding - spent.
Component | Funding ($) | Committed ($) | Spent ($) | Remaining
ZTNA | 2400000 | 1900000 | 1080000 | 1320000
PAM | 900000 | 540000 | 360000 | 540000
SIEM | 1200000 | 200000 | 90000 | 1110000
Program office | 300000 | 150000 | 140000 | 160000
Total | 4800000 | 2790000 | 1670000 | 3130000

## Closure
Program Closure Checklist
Closure item | Owner | Status
All components delivered or formally transferred | PgM | In progress
Benefits handed to BAU owners with measurement plan | Bus Owner | Open
Program-level lessons consolidated | PgM | Open
Financial closure / final reconciliation | Finance | Open
Assurance / sponsor sign-off | SRO | Open
Records archived; team disbanded | PMO | Open