## Dependency Register
Dependency Register — all needs, feeds, and internal dependencies; a dependency is not real until both owners are named and a date is committed
Dep ID | Direction | Giving Team / Program | Giving Deliverable | Receiving Team / Program | Receiving Milestone / Item | Description | Type | Hard / Soft | Criticality | Stage Gate Affected | Need-By Date | Committed Date | Float (days) | Status | Health | Giving Owner | Receiving Owner | Escalation Path | ServiceNow Ref | Last Reviewed | Notes
DEP-01 | Needs | HR / HCM Program | Cleansed worker data feed with manager hierarchy | SailPoint IGA | Joiner-mover-leaver automation build | IGA provisioning logic cannot be built against dirty source data; feed must be cleansed and field-mapped before build starts. | Data | Hard | Gate-Blocking | Build / Test / Validation | 2030-03-17 | 2030-03-03 | 14 | Committed | On Track | [HR data lead] | [IGA PM] | Program Weekly Sync → Steering Committee | RISK-[ID] | 2030-01-30 | Field mapping workshop complete; sample file validated.
DEP-02 | Feeds | Okta SSO | Wave 1 SSO go-live (password-reset volume drop) | Service Desk / ITSM Tooling | Retirement of legacy password-reset scripts | Service Desk holds tooling retirement until Wave 1 stabilizes; they are sequencing their own release around our date. | Technical / Integration | Soft | Milestone | Stabilization / Handoff | 2030-05-15 | 2030-05-08 | 7 | Committed | At Risk | [SSO PM] | [Service Desk lead] | Program Weekly Sync |  | 2030-01-30 | Only one week of float; confirm stabilization exit criteria before their release freeze.
DEP-03 | Internal | SailPoint IGA | Privileged role model (roles + entitlement mapping) | CyberArk PAM | Privileged account onboarding Wave 2 | PAM cannot scope Wave 2 vault onboarding until IGA defines which roles are privileged and who holds them. | Decision / Approval | Hard | Gate-Blocking | Design | 2030-02-24 |  |  | Negotiating | Uncommitted | [IGA PM] | [PAM PM] | Program Weekly Sync → Steering Committee |  | 2030-01-30 | Within 30 days of need-by without commitment — escalate at the Program Weekly Sync.
Note on A2: Unique ID (DEP-01, DEP-02...). Never reuse an ID, even after a row is closed.
Note on B2: Needs = we need this from another team or program. Feeds = another team or program is waiting on this from us. Internal = one program project waits on another.
Note on C2: The team or program delivering the item. Pick the group whose owner can actually commit a date.
Note on D2: The specific thing handed over — a data feed, decision, environment, resource, or document. Name it precisely enough that delivery is unambiguous.
Note on E2: The team or program whose work consumes the deliverable.
Note on F2: The milestone or work item that cannot proceed (or degrades) without the deliverable.
Note on G2: One or two sentences: what is needed and why the receiving work is blocked or at risk without it. Written so someone outside the program understands it.
Note on H2: The nature of the dependency — pick the closest fit. Drives who needs to be in the room to resolve it.
Note on I2: Hard = the receiving work cannot start or finish without it. Soft = the receiving work proceeds, but with risk or degradation.
Note on J2: Gate-Blocking = a stage gate cannot pass without it. Milestone = a milestone slips without it.
Note on K2: The stage gate whose entry or exit criteria this dependency affects. Required for every Gate-Blocking item.
Note on L2: The latest date the receiving team can accept delivery without slipping its milestone or gate.
Note on M2: The date the giving team's named owner has agreed to. Leave blank until a real commitment exists — a hope is not a commitment.
Note on N2: Calculated automatically — do not type here. Need-By Date minus Committed Date, in days. Positive = buffer. Negative = the committed date is later than the date we need it, and we know today rather than at the miss.
Note on O2: Lifecycle: Identified (we know about it) → Negotiating (conversation happening) → Committed (owner agreed to a date) → Closed (delivered and accepted by the receiving team).
Note on P2: Set at each weekly review, consistent with Status: Uncommitted = no committed date yet. On Track = committed and expected to hold. At Risk = committed but confidence is dropping or float is thin. Off Track = will miss or has missed the need-by date.
Note on Q2: Named individual on the giving side — a person, not a team.
Note on R2: Named individual on the receiving side — a person, not a team.
Note on S2: Where this goes if it stalls (e.g., Program Weekly Sync → Steering Committee).
Note on T2: RAID reference in ServiceNow for escalated items. ServiceNow owns actions and decisions; this register owns the dependency view.
Note on U2: Updated at each weekly review. Nothing on the register should be older than one month.
Note on V2: Working notes: negotiation state, conditions on the commitment, context the next reviewer needs.

## Dashboard
Dependency Dashboard — copy charts or tiles directly into status decks
| Open gate-blocking | Gate-blocking, uncommitted | Late commitments (neg. float) | Total open dependencies
| 2 | 1 | 0 | 4
To use in a status deck: click a chart and copy-paste it into PowerPoint (it stays editable), or select the tile area B3:L5 and paste as picture. Charts update automatically as the register changes.

## Summary
Summary — automatic rollups; feeds the executive status deck dependency tags
By Direction
| Needs | 1
| Feeds | 1
| Internal | 1
By Health
| On Track | 1
| At Risk | 1
| Off Track | 0
| Uncommitted | 1
By Status
| Identified | 0
| Negotiating | 1
| Committed | 2
| Closed | 0
Attention Counts
| Open gate-blocking dependencies | 2
| Gate-blocking and not yet committed | 1
| Late commitments (negative float) | 0
Counts include worked example rows until they are replaced with real data.

## PivotSource
Team | Leg | Direction | Dep ID | Status | Health | Need-By | Date Pressure
HR / HCM Program | Giving | Needs | DEP-01 | Committed | On Track | 2030-03-17 | Later
Okta SSO | Giving | Feeds | DEP-02 | Committed | At Risk | 2030-05-15 | Later
SailPoint IGA | Giving | Internal | DEP-03 | Negotiating | Uncommitted | 2030-02-24 | Later
SailPoint IGA | Receiving | Needs | DEP-01 | Committed | On Track | 2030-03-17 | Later
Service Desk / ITSM Tooling | Receiving | Feeds | DEP-02 | Committed | At Risk | 2030-05-15 | Later
CyberArk PAM | Receiving | Internal | DEP-03 | Negotiating | Uncommitted | 2030-02-24 | Later
Formulas:
Need-By = IF([Team]="","",IF('Dependency Register'!L3="","",'Dependency Register'!L3))
Date Pressure = IF([Team]="","",IF([Need-By]="","No Date",IF([Need-By]<TODAY(),"Past Due",IF([Need-By]-TODAY()<=30,"Due ≤30 Days","Later"))))

## Initiative Scorecard
Initiative Scorecard — type an initiative name in the yellow cell; all counts exclude Closed
| Initiative: | SailPoint IGA | Must match the register name exactly. Optional: add a dropdown via Data Validation pointing at your Initiatives list.
Totals
| Total open dependencies | 2
| Giving (this initiative owes) | 1
| Receiving (waiting on others) | 1
By Direction
| Needs | 1
| Feeds | 0
| Internal | 1
By Health
| On Track | 1
| At Risk | 0
| Off Track | 0
| Uncommitted | 1
Date Pressure
| Past Due | 0
| Due ≤30 Days | 0
| No Date | 0