## Cover
Program Workbook — Project Atlas
Worked example: Zero Trust Network Access & Identity Modernization Program
Document version: v1.2 — 2026-04-27
Program Identification
Program name | Project Atlas
Program ID | PROG-2026-001
Strategic theme | Zero Trust Security & Identity Modernization
Executive sponsor | Sandra Park, CISO
Program manager | Senior Security PM (you)
Start date | 2026-01-15
Target end date | 2027-09-30
Total program budget | $8,400,000
Component count | 5 initiatives
Current overall status | At-Risk
Status rationale | Two components At-Risk: ZTNA Rollout (dev tool latency for 10% of users — under remediation) and MFA Hardening (FIDO2 hardware lead time delay — hybrid platform-authenticator approach approved per DC-005). Other 3 components On-Track. Program timeline currently holding. See Status Reports tab for weekly detail.
Last status update | 2026-04-21
Driver | SOC 2 Type II audit findings + 2025 insider threat incident
Regulatory drivers | SOX, GLBA, state privacy laws
What On-Track / At-Risk / Off-Track mean for this program
Status | Definition for Project Atlas
On-Track | On track on scope, schedule, and budget. Risks are within tolerance. No executive escalations needed. If any single component is At-Risk and others are On-Track, program may still be On-Track at PM's discretion.
At-Risk | One or more components have material issues (cost, schedule, scope, or risk) that the team is actively mitigating, BUT the program timeline and budget are still expected to hold. Steering awareness needed; intervention typically not. Trigger: 2+ components At-Risk, OR any single risk rated High/High and unmitigated.
Off-Track | Material risk to program completion timing, budget, or scope. Executive intervention required. Trigger: 2+ components Off-Track, OR any single component Off-Track on a critical-path dependency, OR unrecoverable budget overrun, OR sponsor support materially compromised.
Note: RAG definitions vary by org. The thresholds above are this program's defaults. Adjust to match your org's PMO standards and document the change in the Decisions & Changes log so historical status reports are interpretable.
Workbook Map
# | Tab | Purpose | Update cadence
1 | Cover | Program identification + tab map | Static; updated when material change
2 | Components | 5 component initiatives with status, % complete, budget, risk | Weekly — by program manager
3 | Program RAID | Program-level risks/issues/dependencies (NOT component-level) | Weekly review
4 | Cross-Component Deps | Dependencies between component initiatives | Weekly review
5 | Program Schedule | Milestone roll-up across all components | Weekly update
6 | Program Budget | Total budget with allocation across components | Monthly close
7 | Resource Conflicts | Shared resources allocated across components | Bi-weekly review
8 | Decisions & Changes | Program-level decisions and approved changes | Append as events occur
9 | Action Items | Meeting action items + cross-meeting commitments | Weekly review
10 | Vendor Management | Vendor SLAs, escalations, business reviews, renewals | Monthly + ad-hoc
11 | Benefits Realization | Program benefits map with realization timing | Quarterly review
12 | Status Reports | Program-level weekly status running history | Weekly — append a row
Program vs Project Workbook
This workbook tracks ONE program with 5 component projects. Each component has its own project workbook for component-level detail.
What's HERE: program-level status, cross-component dependencies, shared resources, program-level RAID, program benefits.
What's in the COMPONENT workbooks: component RAID, component schedule, component-level decisions, component team allocation.
Roll-up rule: component status feeds program status. If 2+ components are Off-Track, program status is Off-Track unless explicitly justified otherwise.
RAG dropdowns and conditional formatting auto-apply to status fields throughout. Component status changes turn the cells red/amber/green automatically.
Where to start (new program managers)
1. Fill in the Cover tab — program identification at top, leave the rest as reference.
2. Populate Components tab — list each component initiative with PM, phase, and initial budget. Get sponsor sign-off.
3. Build out Program Schedule — major milestones across components.
4. Identify cross-component dependencies in the Cross-Component Deps tab.
5. Open the Program RAID tab — populate from kickoff risk register; review weekly thereafter.
6. Lock the Program Budget — total approved + per-component allocations + contingency reserve.
7. Map Resource Conflicts — who is on multiple components? Where are over-allocations?
8. Build Benefits Realization map — what value, when, measured how, owned post-program.
9. Establish weekly Status Reports cadence — append a row each week, never overwrite.
10. Decisions & Changes is append-only — log every program-level decision and approved change.
Cross-platform compatibility
Tested in Microsoft Excel and LibreOffice Calc. All formulas use cross-platform compatible functions (no XLOOKUP, IFS, LET).
Conditional formatting (RAG colors) and dropdowns work in Excel, Google Sheets, and LibreOffice. Apple Numbers may render conditional formatting differently — re-apply if importing to Numbers.
Google Sheets import: data validations and most conditional formatting transfer; some EXACT() formula-based formatting may need manual re-creation.
If migrating to Notion / Asana / Smartsheet / Jira, the methodology applies — re-create the tab structures as databases or boards.

## Components
Component Initiatives
The 5 component projects under Project Atlas. Status here rolls up to the program.
# | Component initiative | Component PM | Phase | Status | % complete | Budget ($) | Spend to date ($) | Variance | Top risk | Notes
1 | Identity Provider Migration | M. Ortiz | Execute | On-Track | 65% | 1850000 | 1200000 | 650000 | Legacy app SSO integration risk | On track. 60% of apps migrated to enterprise IdP.
2 | ZTNA Rollout (VPN replacement) | J. Liu | Execute | At-Risk | 45% | 2100000 | 1050000 | 1050000 | Engineering org pilot revealed latency on dev tools | Latency issue mitigated for 90% of cases; 10% need architecture review. Pilot at engineering completes wk of 4/28.
3 | Privileged Access Management | K. Reddy | Plan | On-Track | 20% | 1600000 | 280000 | 1320000 | BeyondTrust vendor SOW negotiation | SOW expected to sign 5/2. Implementation kickoff target 5/15.
4 | MFA Hardening (FIDO2) | S. Chen | Execute | Off-Track | 30% | 1100000 | 680000 | 420000 | FIDO2 hardware procurement delay (12-week lead time) | Hardware delay pushes Phase 2 rollout 8 weeks. Considering hybrid approach with platform authenticators for Phase 1.
5 | Access Review Automation | P. Nguyen | Initiate | On-Track | 10% | 750000 | 35000 | 715000 | Vendor selection pending — RFP closes 5/15 | RFP issued 4/15. 4 vendors confirmed bidding. Scoring complete by 6/1.
| COMPONENT TOTAL |  |  |  | 38.82% | 7400000 | 3245000 | 4155000
Status roll-up rule
Program status reflects component health: if 2+ components are Off-Track, program is Off-Track. If multiple At-Risk without Off-Track, program is At-Risk. All On-Track or 1 At-Risk, program is On-Track. PM judgment overrides this rule when justified — document the reasoning in Status Reports.
% complete methodology
% complete is a PM-asserted estimate of component progress, not strict milestone completion. It accounts for in-progress work within milestones (e.g., ZTNA at 45% reflects pilot underway and architecture work in progress, even though no major milestones are formally complete yet). Discuss methodology change with PMO if you want to switch to strict milestone-weighted or earned-value calculation.
Quick metrics
Components On-Track |  | 3
Components At-Risk |  | 1
Components Off-Track |  | 1
% spend used |  | 43.85%

## Program RAID
Program-Level RAID
Risks/Assumptions/Issues/Dependencies that affect the PROGRAM. Component-specific items live in component workbooks.
ID | Type | Description | Likelihood | Impact | Score | Status | Owner | Date raised | Target close | Mitigation / response plan
P-R-001 | Risk | FIDO2 hardware lead time (12 weeks) jeopardizes program completion timeline | High | High | 9 | Mitigating | S. Chen | 2026-03-15 | 2026-05-30 | Procurement escalation to CFO completed 4/10. Negotiated 50% partial shipment in 6 weeks. Considering platform authenticators for Phase 1 to maintain timeline.
P-R-002 | Risk | Identity Provider migration could break legacy app SSO integrations during ZTNA cutover | Medium | High | 6 | Monitoring | M. Ortiz | 2026-02-20 | 2026-08-30 | Sequencing constraint added: ZTNA rollout follows IdP migration by min 4 weeks per app. Integration test environment built.
P-R-003 | Risk | Engineering org pushback on ZTNA rollout — perceived as friction added to dev workflow | High | Medium | 6 | Mitigating | OCM Lead | 2026-03-01 | 2026-06-30 | OCM activated. CISO + CTO joint message to eng org wk of 4/15. Eng champion network established. Pilot feedback loop in place.
P-I-001 | Issue | PAM tool (BeyondTrust) SOW negotiation stalled on pricing for production database access | — | — |  | Mitigating | Procurement + K. Reddy | 2026-04-10 | 2026-05-02 | Procurement escalation to vendor exec completed 4/22. Counter-proposal expected by 4/28. CFO approved $50K above original budget if needed.
P-D-001 | Dependency | Network team must complete VPN concentrator decommission to free budget for ZTNA expansion | — | — |  | Open | Network Team (J. Park) | 2026-02-15 | 2026-09-30 | Network team committed to Q3 decommission. Tracking in their roadmap. Status check monthly.
P-D-002 | Dependency | HR system access feed required for Access Review Automation | — | — |  | Open | HR IT (A. Brooks) | 2026-04-01 | 2026-07-15 | HR IT prioritization confirmed. API contract signed 4/8. Implementation in their Q2 sprint.
P-A-001 | Assumption | FIDO2 platform authenticators (Touch ID, Windows Hello) acceptable to Compliance for SOX scope | — | — |  | Mitigating | GRC Lead | 2026-04-05 | 2026-04-30 | Compliance review session scheduled 4/26. Initial position: acceptable for non-production access. Production access still requires hardware FIDO2.
P-R-004 | Risk | CISO sponsor departure rumored — could destabilize program priority and budget | Medium | High | 6 | Monitoring | PMO Director | 2026-04-18 | Ongoing | PMO Director and Program Manager aligning with CIO and CTO as backup sponsors. Briefing them weekly on program. Charter unchanged for now.

## Cross-Component Deps
Cross-Component Dependencies
Where Component A needs something from Component B. The most common source of program failure — track these closely.
ID | Source component (needs) | Target component (provides) | What's needed | Need-by date | Status | Risk | Owner | Notes
DEP-001 | ZTNA Rollout (#2) | Identity Provider Migration (#1) | Apps must be migrated to enterprise IdP before ZTNA can apply policy | 2026-08-15 | On-Track | Medium | M. Ortiz | Sequencing built into program schedule. 60% of apps migrated; remaining 40% by 8/1.
DEP-002 | Access Review Automation (#5) | Identity Provider Migration (#1) | Centralized identity needed before access review can run org-wide | 2026-09-30 | On-Track | Low | M. Ortiz | IdP completion 8/30 leaves buffer for access review go-live.
DEP-003 | Access Review Automation (#5) | Privileged Access Management (#3) | PAM must be deployed before privileged access reviews can include those accounts | 2026-10-30 | At-Risk | High | K. Reddy | PAM SOW delay pushes deployment to 9/30. Access Review go-live target 11/15. Tight but achievable.
DEP-004 | MFA Hardening (#4) | Identity Provider Migration (#1) | Enterprise IdP must support FIDO2 (confirmed) before MFA hardening can roll out | 2026-06-30 | Complete | — | M. Ortiz / S. Chen | IdP FIDO2 support enabled 4/15. Dependency satisfied.
DEP-005 | ZTNA Rollout (#2) | Network Team (external — not in program) | VPN concentrator decommission frees network capex for ZTNA expansion | 2026-09-30 | At-Risk | Medium | Network Team / J. Liu | Network team committed but their priorities can shift. Tracked in Program RAID (P-D-001).
DEP-006 | PAM (#3) | MFA Hardening (#4) | FIDO2 hardware tokens needed for privileged users before PAM go-live | 2026-08-30 | At-Risk | High | S. Chen / K. Reddy | FIDO2 hardware delay (P-R-001) puts this at risk. Backup: software token interim, hardware retrofit Phase 2.

## Program Schedule
Program Schedule — Milestones Across All Components
Roll-up of major milestones from each component. Detailed schedules live in component workbooks.
ID | Milestone | Component | Phase | Planned start | Planned end | Actual end | Status | Notes
M-001 | Program kickoff | Program | Initiate | 2026-01-15 | 2026-01-20 | 2026-01-20 | Complete
M-002 | Charter approved by all sponsors | Program | Initiate | 2026-01-20 | 2026-02-05 | 2026-02-03 | Complete
M-003 | IdP RFP issued | IdP Migration | Plan | 2026-01-25 | 2026-02-15 | 2026-02-12 | Complete
M-004 | IdP vendor selected | IdP Migration | Plan | 2026-02-20 | 2026-03-15 | 2026-03-12 | Complete
M-005 | IdP — first 50 apps migrated (Phase 1) | IdP Migration | Execute | 2026-03-20 | 2026-05-30 |  | In Progress | On track — 30 of 50 done
M-006 | IdP — remaining apps migrated (Phase 2) | IdP Migration | Execute | 2026-06-01 | 2026-08-30 |  | Not Started
M-007 | ZTNA pilot — engineering org | ZTNA Rollout | Execute | 2026-04-01 | 2026-04-30 |  | At-Risk | Latency issue under remediation; pilot extended 1 wk
M-008 | ZTNA — wave 1 rollout (eng + product) | ZTNA Rollout | Execute | 2026-05-15 | 2026-07-30 |  | Not Started | Depends on pilot completion
M-009 | ZTNA — wave 2 rollout (corporate) | ZTNA Rollout | Execute | 2026-08-01 | 2026-10-30 |  | Not Started
M-010 | ZTNA — wave 3 (contractors + remaining) | ZTNA Rollout | Execute | 2026-11-01 | 2026-12-31 |  | Not Started
M-011 | PAM SOW signed | PAM | Plan | 2026-04-15 | 2026-05-02 |  | At-Risk | Negotiation stalled (P-I-001)
M-012 | PAM deployment Phase 1 (production servers) | PAM | Execute | 2026-05-15 | 2026-09-30 |  | Not Started
M-013 | PAM deployment Phase 2 (databases + cloud) | PAM | Execute | 2026-10-01 | 2027-01-31 |  | Not Started
M-014 | FIDO2 hardware procurement order placed | MFA Hardening | Plan | 2026-02-15 | 2026-03-15 | 2026-03-12 | Complete
M-015 | FIDO2 hardware delivery (50% partial) | MFA Hardening | Execute | 2026-04-15 | 2026-05-30 |  | Delayed | Partial shipment 6 wks delayed
M-016 | FIDO2 rollout Phase 1 (privileged users) | MFA Hardening | Execute | 2026-06-01 | 2026-07-30 |  | At-Risk | Considering platform authenticators for non-prod
M-017 | FIDO2 rollout Phase 2 (all employees) | MFA Hardening | Execute | 2026-08-01 | 2026-11-30 |  | Not Started
M-018 | Access Review RFP issued | Access Review | Plan | 2026-04-15 | 2026-05-15 |  | In Progress
M-019 | Access Review vendor selected | Access Review | Plan | 2026-05-15 | 2026-06-15 |  | Not Started
M-020 | Access Review go-live (first cycle) | Access Review | Execute | 2026-09-01 | 2026-11-15 |  | Not Started
M-021 | Program closeout & benefits realization plan handoff | Program | Close | 2027-08-01 | 2027-09-30 |  | Not Started

## Program Budget
Program Budget — Allocation Across Components
Total program budget broken down by component. Reserves held at program level for cross-component contingency.
Total approved program budget | 8400000 | Currency | USD | As-of date | 2026-04-21
Allocation | Planned ($) | Committed ($) | Actual to date ($) | Variance ($) | % used | Forecast EAC ($) | Notes
Identity Provider Migration | 1850000 | 1500000 | 1200000 | 650000 | 64.86% | 1820000 | Slight underrun expected — vendor discount
ZTNA Rollout | 2100000 | 1700000 | 1050000 | 1050000 | 50% | 2150000 | Pilot extension may add costs
Privileged Access Management | 1600000 | 120000 | 280000 | 1320000 | 17.5% | 1650000 | SOW negotiation — possibly +$50K
MFA Hardening (FIDO2) | 1100000 | 850000 | 680000 | 420000 | 61.82% | 1180000 | Hardware lead time + interim platform auth
Access Review Automation | 750000 | 80000 | 35000 | 715000 | 4.667% | 730000 | Vendor selection pending
Program management & PMO | 400000 | 150000 | 165000 | 235000 | 41.25% | 390000 | On track
Program contingency reserve | 600000 | 0 | 0 | 600000 | 0% | 500000 | $100K projected use for FIDO2 / PAM
PROGRAM TOTAL | 8400000 | 4400000 | 3410000 | 4990000 | 40.6% | 8420000
Program forecast
Forecast at completion (EAC) | 8420000
Variance at completion (VAC) | -20000
Contingency consumed (forecast) | 100000
Burn rate (avg monthly) | 1136666.6667

## Resource Conflicts
Shared Resources Across Components
People allocated to multiple components. Watch the Total column — anyone over 100% is over-allocated.
Name | Role | IdP | ZTNA | PAM | MFA | Access Review | Program | Total % | Notes
A. Singh | Sr Security Engineer | 30% | 30% | 20% | 10% | 0% | 0% | 90%
L. Garcia | Identity Architect | 60% | 20% | 0% | 20% | 0% | 0% | 100%
R. Patel | Network Engineer | 10% | 50% | 0% | 0% | 0% | 0% | 60%
T. Wilson | GRC Analyst | 10% | 10% | 20% | 20% | 30% | 10% | 100%
D. Kim | Security Engineer | 0% | 20% | 40% | 30% | 0% | 0% | 90%
B. Foster | Cloud Engineer | 20% | 30% | 40% | 20% | 0% | 0% | 110%
E. Tanaka | QA Engineer | 20% | 20% | 20% | 20% | 10% | 0% | 90%
Program PM | Program Manager (you) | 10% | 10% | 10% | 15% | 5% | 50% | 100%
0%
0%
0%
0%
0%
0%
0%
0%
Allocation rules
Total allocation should be ≤100% per person. Anything above is over-allocation and a portfolio risk. 0.9–1.0 (amber) means 'fully booked, no slack' — also a risk because illness or unexpected work has nowhere to go. Surface over-allocations at the program steering meeting.

## Decisions & Changes
Program-Level Decisions & Changes Log
Program-level only. Component-specific decisions live in component workbooks. Append-only — never delete.
ID | Date | Type | Description | Rationale | Decision-maker | Stakeholders consulted | Status
DC-001 | 2026-02-03 | Decision | Selected Okta as enterprise IdP over Azure AD | Okta scored higher on app catalog breadth (60% vs 40% pre-built integrations) and was preferred by business unit IT leads. Total cost slightly higher ($150K over 3 yr) but offset by integration time savings. | Sandra Park (CISO) | CIO, CTO, Identity Architect, Procurement | Active
DC-002 | 2026-02-15 | Change Request — Schedule | Extended ZTNA pilot from 2 weeks to 4 weeks | Engineering org pilot revealed dev-tool latency issues affecting 10% of users. Additional 2 weeks needed to validate fix before broader rollout. | Sandra Park | CTO, ZTNA PM, OCM Lead | Approved
DC-003 | 2026-03-12 | Decision | Adopted BeyondTrust over CyberArk for PAM | BeyondTrust pricing came in $400K under CyberArk over 3 years. Both met functional requirements. BeyondTrust references stronger on cloud / hybrid environments which fits our roadmap. | Sandra Park | CIO, PAM PM, Procurement, Audit | Active
DC-004 | 2026-04-05 | Change Request — Budget | Increased PAM SOW ceiling by $50K to unblock production database access scope | Vendor pricing for production DB tier came in higher than RFP indicated. Required to maintain Phase 1 timeline. Pulled from program contingency reserve. | Sandra Park | CFO, PAM PM, Procurement | Approved
DC-005 | 2026-04-10 | Decision | Approve hybrid FIDO2 approach: hardware tokens for privileged users, platform authenticators (Touch ID, Windows Hello) for everyone else | Hardware lead time was 12 weeks, threatening program timeline. Hybrid approach maintains hardware FIDO2 for SOX-scope users (privileged + production access) and uses platform authenticators for the broader population. Compliance reviewed and accepted 4/26. | Sandra Park | GRC Lead, MFA PM, Audit, IT Operations | Active
DC-006 | 2026-04-21 | Change Request — Scope | Removed legacy mainframe app from IdP migration scope | Mainframe app is 18 months from decommission per IT roadmap. ROI of migrating doesn't justify the integration cost. Application owner confirmed sunset path. | M. Ortiz (IdP PM) | Sandra Park, App Owner, Audit | Approved
DC-007 | 2026-04-15 | Change Request — Schedule | Extended ZTNA pilot 1 additional week (now ending 2026-04-21) | Pilot week 1 surfaced dev tool latency issues for 10% of users. Mitigation deployed but needs validation week before broader rollout decision. Doesn't impact Wave 1 start (still 5/15). | Sandra Park | CTO, ZTNA PM, Eng Champions | Approved

## Action Items
Action Items Tracker
Meeting action items and cross-meeting commitments. Reviewed weekly. Distinct from RAID (issues) and Decisions & Changes.
ID | Date raised | Source meeting / context | Description | Owner | Due date | Priority | Status | Notes
AI-001 | 2026-04-08 | Weekly cross-component standup | M. Ortiz to validate IdP FIDO2 support enabled before MFA Phase 1 starts | M. Ortiz | 2026-04-15 | High | Done | Confirmed 4/15 — DEP-004 closed.
AI-002 | 2026-04-08 | Weekly cross-component standup | J. Liu to schedule architecture review for ZTNA latency edge cases | J. Liu | 2026-04-22 | High | Done | Review held 4/20 — 90% mitigation deployed.
AI-003 | 2026-04-15 | CISO 1:1 | Program PM to draft escalation memo on PAM SOW pricing for CFO awareness | Program PM | 2026-04-23 | Medium | Done | Memo sent 4/22; CFO approved $50K ceiling per DC-004.
AI-004 | 2026-04-15 | Steering committee | OCM Lead to refine engineering pilot feedback summary for next steering | OCM Lead | 2026-04-29 | Medium | In Progress | Survey results in; analysis underway.
AI-005 | 2026-04-21 | Weekly cross-component standup | S. Chen to brief Compliance on FIDO2 hybrid approach scope before 4/26 review | S. Chen | 2026-04-25 | High | In Progress | Pre-brief scheduled 4/24 with GRC Lead.
AI-006 | 2026-04-21 | Program PM weekly with PMO Director | Program PM to align with CIO and CTO as backup sponsors given P-R-004 | Program PM | 2026-05-05 | High | Open | Calendar requests sent. CIO 5/2, CTO 5/5.
AI-007 | 2026-04-21 | Weekly cross-component standup | P. Nguyen to share Access Review RFP scoring rubric with evaluation team | P. Nguyen | 2026-04-28 | Medium | Open
Quick metrics
Open + In Progress |  | 4
Done |  | 3
Blocked |  | 0
Carried Over |  | 0

## Vendor Management
Vendor Management Tracker
Vendors engaged for Project Atlas. Track SLA performance, escalations, business reviews, and renewals.
Vendor | Service / Tool | Component(s) | Contract end | Annual spend ($) | SLA performance | Open escalations | Last business review | Next renewal action | Owner / Account mgr
Okta | Enterprise IdP | IdP Migration | 2028-12-31 | 480000 | On-Track | 0 | 2026-04-02 | Renewal review Q3 2028 | M. Ortiz / Okta acct: J. Park
Zscaler | ZTNA platform (ZIA + ZPA) | ZTNA Rollout | 2029-03-31 | 720000 | At-Risk | 1 (latency for dev tools) | 2026-03-15 | Renewal review Q4 2028 | J. Liu / Zscaler acct: T. Adams
BeyondTrust | PAM platform | PAM | 2029-06-30 | 540000 | On-Track | 1 (SOW pricing — open per P-I-001) | Pending kickoff | First QBR scheduled 2026-08-15 | K. Reddy / BeyondTrust acct: L. Cruz
Yubico | FIDO2 hardware tokens | MFA Hardening | 2027-12-31 | 180000 | Off-Track | 1 (hardware lead time delay — P-R-001) | 2026-03-20 | Quarterly volume review 2026-07-01 | S. Chen / Yubico acct: D. Reyes
SailPoint | Access governance + reviews | Access Review Automation | TBD (vendor selection pending) | 0 | — | — | — | RFP scoring complete by 6/1 | P. Nguyen / TBD
PwC | External audit (SOC 2) | Program (audit support) | 2027-12-31 | 450000 | On-Track | 0 | 2026-02-10 | Annual engagement renewal Q4 2027 | GRC Director / PwC partner: M. Sato
Quick metrics
Total annual vendor spend |  | 2370000
Vendors with open escalations |  | 14
Vendor management discipline
Track every vendor engaged on the program. Escalation count is leading indicator of contract health. Quarterly business reviews surface issues before renewal. Renewal action 6 months ahead of contract end.

## Benefits Realization
Program Benefits Realization Map
Benefits the program is delivering, when each materializes, how it's measured, and who owns sustainment.
Benefit | Source component(s) | Realization timing | Measurement method | Target | Benefit owner (post-program) | Notes
Reduce VPN-related security incidents by 70% | ZTNA Rollout (#2) | 12 months post-launch | Incident count from SIEM tagged 'remote access' | 70% reduction (baseline 2025: 23 incidents) | Director, Security Operations | Measured at 6 mo and 12 mo. Track quarterly.
Achieve SOC 2 Type II audit findings closure for identity controls | IdP Migration (#1) + MFA Hardening (#4) + PAM (#3) | On Phase 1 completion (estimated 9/30) | External auditor attestation | Zero critical/major findings on identity controls in next audit | Director, GRC | Audit window: Q4 2026. Pre-audit dry-run scheduled 8/30.
Reduce mean-time-to-revoke access from 14 days to <24 hours | Access Review Automation (#5) | On launch + 1 quarter (estimated Q1 2027) | Time delta between termination event in HR and access removal across systems | <24 hours for 95% of terminations | Director, Security Operations | HR system feed dependency must be live.
Eliminate password-based access to production systems | PAM (#3) + MFA Hardening (#4) | On Phase 2 completion (estimated 1/31/2027) | Audit log review — count of password auth events on prod systems | Zero password-only access by 2/2027 | Director, Infrastructure | Hard cutover requires PAM Phase 2 + FIDO2 Phase 2 both complete.
Reduce identity-related help desk tickets by 40% | IdP Migration (#1) + MFA Hardening (#4) | 6 months post-launch | ServiceNow ticket volume tagged 'identity' or 'MFA' | 40% reduction (baseline 2025 monthly avg: 340) | Director, IT Service Management | Counter-effect possible during migration — expect spike before drop.
Enable foundation for future Zero Trust architecture | All 5 components | On program completion (estimated 9/30/2027) | Architecture maturity assessment by external advisor | Achieve 'Defined' or higher on 8 of 10 ZT pillars | VP, Security Architecture | Strategic, not directly measurable. Maturity assessment Q4 2027.
Reduce annual cost of legacy VPN infrastructure | ZTNA Rollout (#2) | On VPN decommission (estimated 12/31/2026) | Annual VPN licensing + maintenance contracts cancelled | $420K annual savings | VP, Network Engineering | Dependent on Network team's decommission timeline (P-D-001).

## Status Reports
Program Status Reports — Running History
Append a new row each week. The history is the artifact — never overwrite.
Report date | Period | Reported by | Overall status | Key accomplishments | Planned next period | Top risks / issues | Asks / blockers
2026-04-07 | Wk 14 | Program PM | At-Risk | IdP migration hit 50% of Phase 1 apps. ZTNA pilot launched eng org. PAM SOW kickoff with BeyondTrust this week (vendor selected 3/12 — DC-003). | Continue IdP Phase 1; ZTNA pilot week 1 feedback session; PAM SOW negotiation kickoff with vendor. | FIDO2 hardware lead time delay (P-R-001) — 12 wk lead time confirmed. Engineering pushback on ZTNA (P-R-003) emerging. | Need CISO 1:1 with CTO this week to align on ZTNA enforcement timing for engineering org.
2026-04-14 | Wk 15 | Program PM | At-Risk | ZTNA pilot week 1 complete. Latency issue identified for dev tools (10% of users). PAM SOW negotiation underway. FIDO2 procurement escalation to CFO complete — partial shipment negotiated. | ZTNA latency fix deployment; pilot extension through wk of 4/21 (DC-002). Continue PAM SOW. Begin Access Review RFP draft. | ZTNA latency mitigation pending architecture review. PAM SOW pricing higher than RFP indicated. | Need approval on PAM SOW $50K ceiling increase from program contingency (taken to steering 4/16).
2026-04-21 | Wk 16 | Program PM | At-Risk | ZTNA latency mitigation deployed for 90% of cases. PAM SOW $50K increase approved (DC-004). FIDO2 hybrid approach decided (DC-005) — Compliance review scheduled 4/26. Mainframe app removed from IdP scope (DC-006). Access Review RFP issued 4/15. | Complete ZTNA pilot extended period; finalize architecture review for remaining 10% latency cases; PAM SOW signature target 5/2; Compliance review of FIDO2 hybrid approach. | PAM SOW signature still pending (P-I-001). FIDO2 hybrid approach awaiting Compliance review. CISO sponsor departure rumor (P-R-004) being monitored. | None this week. PAM SOW expected to close by 5/2 without further escalation.