## Document Control
Stakeholder Assessment — Document Control
| Program | [Program name]
| Artifact | Stakeholder Assessment
| Version | v1.0 — Final template for OCM team use
| Owner | OCM Lead
| Reviewers | Program Manager; Communications Lead
| Approver | Program Sponsor
| Last revised | [date]
| Refresh cadence | Reassess support levels at each program phase and before every readiness gate; a stakeholder assessment done once is a snapshot, not a strategy.
| Confidentiality | Support-level ratings are working judgments for the OCM team. Restrict distribution; never publish individual ratings outside the program office.
| Linked artifacts | Communications Plan — the seven audiences here mirror the plan; engagement channels align to the plan's calendar
Message House (Safer / Simpler / Ready) — the Primary Message Pillar column ties each stakeholder's engagement to the pillar that answers their concern
Sponsor Action Roadmap — Sponsor Coalition Say / Attend / Sign columns feed the roadmap directly
Change Impact Assessment workbook — Audience IDs are keyed to its Audience Inventory

## Instructions
Stakeholder Assessment — Instructions & Method
Purpose
This workbook identifies the individuals whose influence and support determine adoption, assesses where each stands today versus where the program needs them, and converts the gap into an engagement strategy and a working sponsor coalition.
Alignment to the Communications Plan
Every stakeholder is keyed to one of the seven Communications Plan audiences via Audience ID. Engagement channels and frequency should align to the plan's calendar so stakeholders hear one coordinated program voice, with 1:1 engagement layered on top for Critical and High priority individuals. The Primary Message Pillar column ties each stakeholder's talking points to the Message House pillar — Safer, Simpler, or Ready — that best answers their concern.
How the tabs connect
1. Stakeholder Register — one row per named individual, keyed to an Audience ID from the Change Impact Assessment workbook.
2. Stakeholder Assessment — rate influence and impact, then record current and desired engagement. Engagement Gap, Engagement Priority, and Quadrant calculate automatically.
3. Engagement Strategy — concerns, what they gain, message pillar, channel, frequency, owner, and a dated next action per stakeholder. The Quadrant column pulls from the assessment to set the default posture.
4. Sponsor Coalition — the sponsor cascade with Say / Attend / Sign actions per sponsor, feeding the Sponsor Action Roadmap in the Communications Plan. Sponsor Follow-Through tracks delivery of those commitments — action, not attitude.
5. Summary Dashboard — automatic counts by engagement level, engagement priority, and quadrant for status reporting and gate reviews.
6. Reference Data — scoring scales used by the formulas. Do not edit.
Scales
Influence: weight in decisions, budgets, and opinion-shaping. Impact on Stakeholder: how much the change affects their world — align to the Change Impact Assessment rating for their audience group. Engagement: Disengaged, Neutral, Engaged, Advocating, scored 1 to 4. Engagement Gap = where you need them minus where they are today; a positive number means this person needs deliberate engagement to move.
Engagement Priority: Critical = high influence with any positive gap. High = high influence, or a gap of two or more levels. Medium = any other positive gap. Maintain = no gap; keep support from eroding.
Quadrant (influence by impact): Manage Closely, Keep Satisfied, Keep Informed, Monitor. The quadrant is the default posture; the Engagement Strategy tab is where you tailor it.
Operating rhythm
Build the register at program kickoff from the Audience Inventory — every audience needs at least one named stakeholder. Reassess engagement at each phase and before every readiness gate. Bring the Summary Dashboard and the Critical list to sponsor check-ins. Resistance is information: record the concern in Engagement Strategy and answer it — an unanswered objection does more damage than a voiced one.
Quality bar
Every Critical or High priority stakeholder has a named engagement owner and a dated next action. Every audience group has at least one stakeholder in the register. Every Disengaged stakeholder with high influence has a Sponsor Coalition entry.
Legend
White cell = enter data ¦ Grey cell = formula, do not edit ¦ Red / Amber / Green = attention / watch / healthy ¦ Italic row = worked example, replace with real data

## Reference Data
Reference Data — scales used by formulas (do not edit)
Engagement Level | Score | Definition
Disengaged | 1 | Not paying attention or actively opposed; raises objections or works around the change.
Neutral | 2 | Aware but uncommitted; complies passively without advocating.
Engaged | 3 | Participates willingly and speaks positively about the change when asked.
Advocating | 4 | Actively promotes the change, removes barriers, and influences others toward adoption.
Audience ID |  | Audience Group (mirrors the Communications Plan and Change Impact Assessment)
AUD-01 |  | Executive Leadership
AUD-02 |  | People Leaders
AUD-03 |  | Frontline Staff
AUD-04 |  | General Workforce
AUD-05 |  | IT & Application Owners
AUD-06 |  | Help Desk Teams
AUD-07 |  | External Partners

## Stakeholder Register
Stakeholder Register — one row per named individual, keyed to a Communications Plan audience
Stakeholder ID | Name | Title / Role | Organization / Team | Audience ID | Audience Group | Relationship Owner | Notes
STK-01 | J. Chen | Director, Applications | IT | AUD-05 | IT & Application Owners | Program Manager | Chairs the app-owner council; trusted voice with operational leadership.

## Stakeholder Assessment
Stakeholder Assessment — influence, impact, and the engagement gap that drives priority
Stakeholder ID | Name | Influence | Impact on Stakeholder | Current Engagement | Desired Engagement | Engagement Gap | Engagement Priority | Quadrant
STK-01 | J. Chen | High | High | Neutral | Advocating | 2 | Critical | Manage Closely

## Engagement Strategy
Engagement Strategy — tailored plan per stakeholder; pillar ties talking points to the Message House
Stakeholder ID | Name | Quadrant (auto) | Key Concerns | What They Gain | Primary Message Pillar | Preferred Channel | Frequency | Engagement Owner | Next Action | Next Action Date | Status
STK-01 | J. Chen | Manage Closely | Testing load on app owners during a competing upgrade window; fears service disruption at cutover. | Single access model reduces owner support tickets; earlier visibility into wave schedules. | Simpler | 1:1 meeting | Biweekly | Program Manager | Walk through the Wave 1 test calendar and agree the validation deadline. | [YYYY-MM-DD] | Open

## Sponsor Coalition
Sponsor Coalition — the sponsor cascade; Say / Attend / Sign feeds the Sponsor Action Roadmap
Sponsor Name | Sponsor Level | Audience Groups Covered | Say (messages the sponsor delivers) | Attend (moments the sponsor shows up) | Sign (approvals and recognitions the sponsor owns) | Timing / Phase | Sponsor Follow-Through | Coaching Needs | Coalition Owner
M. Okafor | Cascading | IT & Application Owners | Opens the Wave 1 briefing; reinforces the validation deadline at the monthly leaders meeting. | Wave readiness review; first go-live morning check-in. | Signs the wave validation certificate; recognizes completed app owners by name. | [Wave 1 window] | Consistent | Talking points and a one-page wave summary before each leaders meeting. | OCM Lead
Note on B2: Sponsor tiers: Executive — owns the outcome; sets direction and lends visible authority to the program. Cascading — leaders who carry the message through their organizations and hold their teams to the asks. Local — closest to affected teams; reinforces day to day and surfaces resistance early.

## Summary Dashboard
Summary Dashboard — automatic counts for status reporting and gate reviews
Current Engagement Level
| Disengaged | 0
| Neutral | 1
| Engaged | 0
| Advocating | 0
Engagement Priority
| Critical | 1
| High | 0
| Medium | 0
| Maintain | 0
Quadrant
| Manage Closely | 1
| Keep Satisfied | 0
| Keep Informed | 0
| Monitor | 0
Open Next Actions
| Open | 1
| In Progress | 0
Counts include worked example rows until they are replaced with real data.