## Document Control
Change Impact Assessment — Document Control
| Program | [Program name]
| Artifact | Change Impact Assessment
| Version | v1.0 — Final template for OCM team use
| Owner | OCM Lead
| Reviewers | Program Manager; Communications Lead; Project Managers
| Approver | Program Sponsor
| Last revised | [date]
| Refresh cadence | Reassess at the entry to each stage gate and before every readiness gate; update within five business days of any scope or wave change.
| System of record note | RAID items, decisions, and tasks arising from this assessment are logged in ServiceNow. This workbook owns impact analysis only.
| Linked artifacts | Communications Plan (audiences, phase arc, calendar) — audience segmentation in this workbook mirrors the plan's seven audiences
Message House (Safer / Simpler / Ready) — behavior-change statements feed message content
Sponsor Action Roadmap (Say / Attend / Sign) — sponsor actions in Readiness Requirements feed the roadmap
Readiness Gates — Readiness Requirements and Traceability feed go / no-go criteria
Stakeholder Assessment workbook — stakeholder register is keyed to the audience IDs in this workbook

## Instructions
Change Impact Assessment — Instructions & Method
Purpose
This workbook identifies every audience group touched by the program's changes, rates the impact across seven dimensions, and converts those findings into readiness requirements, resistance mitigations, and traceable inputs to the Communications Plan, training plan, and readiness gates.
Alignment to the Communications Plan
The Audience Inventory is pre-populated with the seven audiences defined in the Communications Plan. Do not rename audiences here without updating the Communications Plan — the two artifacts must segment identically or messages and impacts will not trace. The Behavior Change column on the Impact Assessment tab is the raw material for the Message House; the Communication Touches column on Readiness Requirements feeds the plan's calendar; the Traceability tab confirms the loop is closed.
How the tabs connect
1. Change Summary — pre-seeded with the program's four workstream changes. Refine descriptions and add wave-level rows as scope firms up.
2. Audience Inventory — pre-seeded with the seven Communications Plan audiences. Add headcount, point of contact, and cascading sponsor; split an audience only if the split will receive different messages or training.
3. Impact Assessment — rate each change-audience pair across the seven impact dimensions using the Rating Criteria definitions. Impact Score and Overall Impact calculate automatically.
4. Rating Criteria — High / Medium / Low definitions per dimension so ratings are comparable across raters and projects.
5. Readiness Requirements — the training, access, communication touches, and sponsor actions each audience needs before its mapped stage gate.
6. Resistance & Risk — audience-level adoption risks (change fatigue, competing initiatives, prior pushback) with mitigation owners.
7. Traceability — confirms each audience traces to a Communications Plan entry, a training item, and a readiness gate criterion. The Trace Status column flags gaps automatically.
8. Impact Summary — automatic counts for status reporting and gate reviews.
Operating rhythm
Run the full assessment during Design for each wave. Reassess at the entry to Build / Test / Validation and again before Operational Readiness / Go-Live. One rater drafts, a second reviews, and the OCM Lead calibrates ratings across audiences before publishing. Bring the Impact Summary and open trace gaps to every readiness gate review.
Quality bar
Every audience row generates at least one communications entry, training item, or readiness gate criterion — if it generates none, remove it. Every High overall impact has a named sponsor action and a stage gate mapping. Ratings cite the Rating Criteria definitions, not rater instinct.
Legend
White cell = enter data ¦ Grey cell = formula, do not edit ¦ Red / Amber / Green = High / Medium / Low ¦ Italic row = worked example, replace with real data ¦ Pre-seeded rows = starting data from the Communications Plan and program scope, refine as needed

## Rating Criteria
Rating Criteria — apply these definitions on the Impact Assessment tab
Impact Dimension | High (3) | Medium (2) | Low (1)
Process & Workflow | Core daily workflow is redesigned or replaced; the group cannot perform the process the old way after go-live. | Notable steps change within an existing workflow; workarounds exist for a transition period. | Minor step or sequence changes; the group could self-discover the change with light guidance.
Tools & Systems | Primary system is replaced or a new system becomes mandatory for daily work. | Significant new features, screens, or integrations in an existing system. | Cosmetic or infrequent system changes; no new login or interface to learn.
Skills & Knowledge | New skills required that need formal training and practice before go-live. | Existing skills extended; short instructor-led or guided sessions close the gap. | Awareness-level knowledge only; a job aid or announcement is sufficient.
Roles & Responsibilities | Roles are created, eliminated, or accountability moves between teams. | Responsibilities shift within existing roles; approval paths or handoffs change. | No accountability change; minor task ownership adjustments.
Effort & Time | Sustained additional effort, or significant one-time effort during cutover that displaces normal duties. | Moderate one-time effort (testing, validation, migration tasks) absorbed within normal capacity. | Minimal effort; participation limited to reading communications or brief actions.
Risk Exposure | Failure by this group directly threatens go-live, compliance, customer or mission-critical service, or security posture. | Failure creates rework, delay, or degraded service that is recoverable within the wave. | Failure has limited, contained consequences with simple recovery.
Downstream Impact | Other groups or systems cannot proceed or operate if this group is not ready (widest reach). | One or two dependent groups or systems are delayed if this group is not ready. | No dependent groups or systems rely on this group's readiness.

## Change Summary
Change Summary — pre-seeded with program workstreams; add wave-level rows as scope firms up
Change ID | Change Name | Description | Current State | Future State | Go-Live / Wave | Change Owner | Status
CH-01 | SSO Consolidation | Consolidate application sign-in onto the enterprise single sign-on platform, retiring separate credentials wave by wave. | [describe how this works today] | [describe the target state] |  |  | Planned
CH-02 | MFA Enforcement | Enforce multi-factor authentication across the workforce and partner access paths. | [describe how this works today] | [describe the target state] |  |  | Planned
CH-03 | IGA Rollout | Introduce identity governance for access requests, approvals, and certifications. | [describe how this works today] | [describe the target state] |  |  | Planned
CH-04 | Privileged Access Onboarding | Bring privileged accounts under vaulting, session management, and just-in-time access controls. | [describe how this works today] | [describe the target state] |  |  | Planned

## Audience Inventory
Audience Inventory — the seven Communications Plan audiences; segment further only if the split gets different messages or training
Audience ID | Audience Group | Description | Headcount | Location(s) | Point of Contact | Cascading Sponsor | Concurrent Change Load
AUD-01 | Executive Leadership | Executives who sponsor the program, approve investment, and set the tone for adoption across the organization. |  |  |  |  | [other initiatives hitting this audience in the same window]
AUD-02 | People Leaders | Managers and supervisors who cascade messages, prepare their teams, and absorb first-line questions and resistance. |  |  |  |  | [other initiatives hitting this audience in the same window]
AUD-03 | Frontline Staff | Frontline staff whose daily workflow depends on uninterrupted access to core operational applications; lowest tolerance for disruption. [Adjust for client: clinical staff, branch staff, plant operators.] |  |  |  |  | [other initiatives hitting this audience in the same window]
AUD-04 | General Workforce | All remaining staff whose sign-in, access request, and credential experience changes. |  |  |  |  | [other initiatives hitting this audience in the same window]
AUD-05 | IT & Application Owners | Application owners and IT teams accountable for integration, testing, and validation of each wave. |  |  |  |  | [other initiatives hitting this audience in the same window]
AUD-06 | Help Desk Teams | Front-line support absorbing call volume at each wave; need scripts, knowledge articles, and escalation paths before go-live. |  |  |  |  | [other initiatives hitting this audience in the same window]
AUD-07 | External Partners | Vendors, affiliates, and partner organizations whose access paths or federation change. |  |  |  |  | [other initiatives hitting this audience in the same window]

## Impact Assessment
Impact Assessment — rate each change-audience pair using the Rating Criteria; Behavior Change feeds the Message House
Change ID | Audience ID | Audience Group | Process & Workflow | Tools & Systems | Skills & Knowledge | Roles & Responsibilities | Effort & Time | Risk Exposure | Downstream Impact | Impact Score | Overall Impact | Timing of Impact | Duration | Behavior Change (From → To)
CH-01 | AUD-05 | IT & Application Owners | High | High | Medium | Medium | High | High | High | 2.7 | High | Before Go-Live | One-Time | From validating logins app-by-app with local credentials → to validating role-based access through SSO test plans before each wave.

## Readiness Requirements
Readiness Requirements — what each audience needs before its stage gate; sponsor actions feed the Sponsor Action Roadmap
Audience ID | Audience Group | Training Required | Access / Provisioning | Communication Touches | Sponsor Actions (feed Sponsor Action Roadmap) | Stage Gate | Readiness Criterion | Owner | Due Date | Status
AUD-05 | IT & Application Owners | SSO validation test-plan workshop (90 min) with hands-on practice check, plus validation job aid. | Test-tenant access provisioned for all app owners two weeks before wave testing opens. | Workshop invitation three weeks out, reminder one week out, testing-window kickoff note — all scheduled in the Communications Plan calendar. | Cascading sponsor opens the workshop invitation (Say), attends the testing kickoff (Attend), and confirms training completion at the leaders meeting (Sign). | Build / Test / Validation | 100% of app owners pass the hands-on check and are provisioned before wave testing opens. | OCM Lead | [YYYY-MM-DD] | In Progress

## Resistance & Risk
Resistance & Risk — audience-level adoption risks; escalate program-level items to ServiceNow RAID
Flag ID | Audience Group | Flag Type | Description | Likelihood | Impact if Unmanaged | Mitigation | Mitigation Owner | ServiceNow RAID Ref | Status
FL-01 | IT & Application Owners | Competing Initiative | Major application upgrade testing overlaps the Wave 1 validation window, splitting owner capacity. | High | High | Sequence Wave 1 validation to close one week before the upgrade testing opens; escalate conflicts through the cascading sponsor. | Program Manager | RISK-[ID] | Open

## Traceability
Traceability — every audience maps to a Communications Plan entry, a training item, and a readiness gate criterion
Audience ID | Audience Group | Communications Plan Entry (phase & calendar row) | Training Item | Readiness Gate Criterion | Trace Status
AUD-05 | IT & Application Owners | Communications Plan: Action phase — wave briefing, testing digest, go-live confirmation | SSO test-plan workshop + validation job aid | Go-Live gate: 100% Wave 1 applications validated and signed off | Complete

## Impact Summary
Impact Summary — automatic counts for gate reviews and status reporting
Overall Impact (change-audience pairs)
| High | 1
| Medium | 0
| Low | 0
Timing of Impact
| Before Go-Live | 1
| During Testing | 0
| At Go-Live | 0
| Post-Stabilization | 0
Readiness Requirement Status
| Not Started | 0
| In Progress | 1
| Complete | 0
| At Risk | 0
Traceability
| Gap | 0
| Complete | 1
Open Resistance Flags
| Open | 1
| Mitigating | 0
Counts include worked example rows until they are replaced with real data.