## Cover
PMO Project Workbook
Single source of truth for one project. All tabs reference this project.
Document version: v1.2 — 2026-04-27
Project Identification
Project name
Project ID / code
Project sponsor
Project manager / PM
Department / function
Customer / business unit
Start date
Target end date
Approved budget
Phase
Current overall status
Status rationale
Last status update
What On-Track / At-Risk / Off-Track mean
Status | Definition for this project
On-Track | On track on scope, schedule, and budget. Risks within tolerance. No executive escalations needed.
At-Risk | Material issues being actively mitigated, BUT project timeline and budget still expected to hold. Sponsor and steering awareness needed; intervention typically not. Trigger: high-impact risk unmitigated, OR material variance on any single dimension (cost/schedule/scope).
Off-Track | Material risk to project completion timing, budget, or scope. Executive intervention required. Trigger: critical-path slip with no recovery plan, OR unrecoverable budget overrun, OR material scope reduction needed, OR sponsor support compromised.
Note: RAG definitions vary by org. Adjust to your PMO's standards and document the change in the Decisions & Changes log so historical status reports remain interpretable.
Workbook Map
# | Tab | Purpose | When you use it
1 | Cover | Project ID and tab map | Always — top-level reference
2 | Charter | Business case, scope, objectives, success criteria, sign-offs | Initiate phase; reference throughout
3 | Stakeholders | Stakeholder register and engagement plan | Initiate / Plan; update as it changes
4 | RACI | Decision-level accountability matrix with auto-validation | Plan phase; revisit on org changes
5 | Requirements | Business + technical requirements, traced to design and test | Plan onward; foundation for UAT
6 | RAID Log | Risks, Assumptions, Issues, Dependencies — single integrated log | Plan onward; weekly review
7 | Schedule | Milestones, deliverables, dates, dependencies, status | Plan onward; weekly update
8 | Resources | Team roster, allocation %, type, rate, summary metrics | Plan onward; weekly review
9 | Budget | Budget by category, planned vs actual, variance, forecast | Plan onward; monthly close
10 | Decisions & Changes | Combined log: decisions made AND approved scope/schedule/budget changes | Throughout — append as decided/approved
11 | Action Items | Meeting action items + cross-meeting commitments | Throughout — review weekly
12 | Vendor Management | Vendor SLA, escalations, business reviews, renewals | Monthly + ad-hoc
13 | Status Reports | Weekly status snapshots — running history | Weekly — append a new row
14 | UAT Log | Test cases, execution results, entry/exit criteria | Test & deploy phase
15 | Post-Incident Actions | Cross-incident corrective action tracker with verification | Standalone — used by all post-incident reviews
16 | Lessons Learned | Captured throughout the project, formalized at close | Throughout, formalized at close
17 | Closeout | Final outcomes, benefits realization, archive pointers | Close phase only
How to Use This Workbook
1. Fill in the Cover tab first — every other tab assumes the project ID is set.
2. Tabs follow lifecycle order: Initiate → Plan → Execute → Test → Close.
3. The RAID Log replaces separate Risk, Assumption, Issue, and Dependency tabs.
4. Decisions & Changes is one combined tab — filter by Type column to see decisions vs change requests.
5. Action Items are distinct from RAID — meeting/working commitments with a name and a date, separate from risks/issues.
6. Status Reports, Decisions & Changes, and Action Items are append-only. Never overwrite past entries.
7. RACI integrity: the # of A's column flags activities that don't have exactly one Accountable.
8. Requirements Trace: Must Have requirements without test cases are flagged in the summary.
9. Post-Incident Actions is a standalone, cross-incident tracker — not project-specific.
10. Vendor Management tab tracks vendors engaged on this project — SLAs, escalations, renewal dates.
Known artifact overlap: stakeholder data
Stakeholder identification lives in the Stakeholders tab — name, role, classification, RACI level.
When you build a Communications Plan (separate doc), the Audience Map will need many of the same names.
Discipline: keep stakeholder identification authoritative in the Stakeholders tab. Keep channel/cadence specifics in the Comms Plan.
Review for consistency at monthly planning. If a stakeholder changes role, update both.
Cross-platform compatibility
Tested in Microsoft Excel and LibreOffice Calc. All formulas use cross-platform compatible functions (no XLOOKUP, IFS, LET).
Conditional formatting (RAG colors) and dropdowns work in Excel, Google Sheets, and LibreOffice. Apple Numbers may render conditional formatting differently — re-apply if importing to Numbers.
If migrating to Notion / Asana / Smartsheet / Jira, the methodology applies — re-create the tab structures as databases or boards.

## Charter
Project Charter
The foundational document. Approved at kickoff, referenced throughout.
Project name | Pulled from Cover tab
Project sponsor | Executive accountable for project success
Project manager / PM | Person running the project day-to-day
Date | Charter version date
Version | v1.0, v1.1, etc.
BUSINESS CASE
Problem / opportunity | What problem are we solving?
Strategic alignment | Which corporate goal or OKR does this support?
Expected business value | Revenue, cost savings, efficiency, risk mitigation — quantified
Cost of not doing | What happens if we don't do this?
OBJECTIVES & SUCCESS CRITERIA
Project objectives | 3–5 SMART objectives
Success criteria | How we'll know we succeeded — measurable
KPIs / metrics | Specific metrics with targets
SCOPE
In scope | What this project will deliver
Out of scope | Explicitly what this project will NOT deliver
Assumptions | Working assumptions
Constraints | Time, budget, technical, regulatory, organizational
DELIVERABLES & MILESTONES
Major deliverables | Top-level outputs
Key milestones | Top-level dates
STAKEHOLDERS & GOVERNANCE
Sponsor | Final decision authority
Steering committee | Names + roles
Decision-making model | Consensus, sponsor decides, etc.
Escalation path | Who escalates to whom
BUDGET
Approved budget | Total approved
Funding source | Department, program, capex, opex
Budget authority | Who can approve overages
HIGH-LEVEL RISKS
Top risks at kickoff | Top 3–5 risks
APPROVALS
Sponsor approval | Name, date, signature
PMO approval | Name, date
Finance approval | Name, date
Other approvals | Legal, security, compliance as required

## Stakeholders
Stakeholder Register & Engagement Plan
Who matters, what they need, how we engage them.
Name | Role / Title | Org / Department | Influence | Interest | RACI | Engagement level | Preferred channel | Communication needs / cadence

## RACI
RACI Matrix
Activities/decisions in rows, roles in columns. Exactly ONE A per row.
Activity / Decision | Sponsor | PM | Eng Lead | QA Lead | Business / PO | Security | Compliance / Legal | Vendor | # of A's
Approve project charter | [8 empty] | 0
Approve scope changes | [8 empty] | 0
Approve budget changes | [8 empty] | 0
Approve schedule changes | [8 empty] | 0
Approve vendor selection | [8 empty] | 0
Sign off on requirements (BRD) | [8 empty] | 0
Sign off on technical design | [8 empty] | 0
Approve UAT entry / exit criteria | [8 empty] | 0
Approve go-live / production deployment | [8 empty] | 0
Approve security review | [8 empty] | 0
Approve compliance review | [8 empty] | 0
Approve customer / external communications | [8 empty] | 0
Resolve P0/P1 issues during execute | [8 empty] | 0
Approve project closeout | [8 empty] | 0
Approve benefits realization plan | [8 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Field guide
R — Responsible | Does the work. Multiple R's allowed.
A — Accountable | Owns the outcome. Exactly ONE A per row. The buck stops here.
C — Consulted | Provides input before the decision. Two-way comms.
I — Informed | Notified after the decision. One-way comms.
R/A or A/R | Same person both responsible and accountable. Use sparingly.

## Requirements
Requirements Traceability Matrix
Every business and technical requirement, traced from source through design to test.
ID | Type | Requirement description | Source | Priority | Status | Owner | Linked design / spec | Linked test case | UAT result
Coverage summary
Total requirements |  | 0
Must Have count |  | 0
Approved or in progress |  | 0
UAT pass rate |  | 0%
Must Have requirements without test case |  | 0

## RAID Log
RAID Log — Risks, Assumptions, Issues, Dependencies
Single integrated log. Filter by Type column to view a specific category.
ID | Type | Description | Likelihood | Impact | Score | Status | Owner | Date raised | Target close | Mitigation / response plan

## Schedule
Schedule — Milestones & Deliverables
Top-level project schedule. Detailed task management lives in Jira / Smartsheet / MS Project.
ID | Milestone / deliverable | Owner | Phase | Planned start | Planned end | Actual end | Status | Dependencies / notes

## Resources
Resource Plan
People allocated to this project.
Name | Role on project | Home department | Type | Allocation % | Start date | End date | Hourly / loaded rate | Notes
Allocation summary
Total FTE allocation | 0
Total contractor allocation | 0
Headcount on project | 0

## Budget
Budget — Planned vs Actual
Track approved budget against actual spend. Update at month-end close.
Total approved budget |  | Currency | USD | As of date
Category | Planned ($) | Committed ($) | Actual to date ($) | Variance ($) | % used | Notes
Labor — internal |  |  |  |  | 0%
Labor — contractors |  |  |  |  | 0%
Vendors / SOWs |  |  |  |  | 0%
Software & tools |  |  |  |  | 0%
Hardware / infrastructure |  |  |  |  | 0%
Travel |  |  |  |  | 0%
Training |  |  |  |  | 0%
Communications & marketing |  |  |  |  | 0%
Contingency |  |  |  |  | 0%
Other |  |  |  |  | 0%
0%
0%
TOTAL | 0 | 0 | 0 | 0 | 0%

## Decisions & Changes
Decisions & Changes — Combined Log
Append-only log of decisions made AND approved scope/schedule/budget changes. Filter by Type.
ID | Date | Type | Title / decision / change | Rationale | Owner / decision-maker | Schedule impact (days) | Budget impact ($) | Scope impact | Approver | Status
Field guide
Type | Decision = a choice made (vendor, design, scope clarification). Change Request = a formal modification to the approved baseline (charter scope, schedule, budget). Filter by this column.
Decisions | Don't need a formal approval workflow. Just need to be recorded. Status = Active / Superseded / Reversed.
Change Requests | Go through workflow: Submitted → Under Review → Approved / Rejected → Implemented. Schedule and budget impact are required.
Append-only | Never delete entries. If a decision is reversed or change is undone, mark superseded/reversed and add a new row.

## Action Items
Action Items Tracker
Meeting action items and cross-meeting commitments. Reviewed weekly. Distinct from RAID (issues) and Decisions & Changes.
ID | Date raised | Source meeting / context | Description | Owner | Due date | Priority | Status | Notes
Quick metrics
Open + In Progress |  | 0
Done |  | 0
Blocked |  | 0
Carried Over |  | 0

## Vendor Management
Vendor Management Tracker
Vendors engaged on this project. Track SLA performance, escalations, business reviews, and renewals.
Vendor | Service / Tool | Contract end | Annual spend ($) | SLA performance | Open escalations | Last business review | Next renewal action | Owner / Account mgr
Quick metrics
Total annual vendor spend |  | 0
Vendor management discipline
Track every vendor engaged on the project. Escalation count is leading indicator of contract health. Quarterly business reviews surface issues before renewal. Renewal action 6 months ahead of contract end.

## Status Reports
Status Reports — Running History
Append a new row each reporting cycle. This is the historical record.
Report date | Reporting period | Reported by | Overall status | Key accomplishments this period | Planned for next period | Top risks / issues | Asks / blockers

## UAT Log
UAT Test Case Log
Each row is one test case run. Pass rate auto-calculates for exit criteria.
UAT Entry / Exit Criteria
Entry criteria met (Y/N + date)
Exit criteria target (% pass)
Actual pass rate | 0%
UAT lead
UAT period
Sign-off received from
Test Cases
Test ID | Test case description | Linked req (ID from Requirements tab) | Test data / preconditions | Expected result | Tester | Test date | Result | Defect ID (if Fail) | Notes
Test execution summary
Total test cases |  | 0
Pass |  | 0
Fail |  | 0
Blocked |  | 0
Not Run |  | 0
Pass rate (Pass / Pass+Fail) |  | 0%
Defects open (rows with Defect ID) |  | 0

## Post-Incident Actions
Post-Incident Action Tracker
Cross-incident corrective actions with verification. Standalone tracker — used by all post-incident reviews.
Tracker summary
Total open actions | 0 | Overdue | 0 | Done — awaiting verification | 0 | Verified effective | 0 | Re-incidents detected | 0
Corrective actions
Action ID | Incident ID | Severity | Type | Action description | Tied to root cause | Owner | Due date | Priority | Status | Verification result | Re-incident? (verification check) | Notes
Field guide
Action ID | Sequential — PIA-001, PIA-002, etc.
Incident ID | Cross-reference to the incident this action came from. One incident may have multiple actions; one action may address multiple incidents.
Type | Code fix: specific bug. Infrastructure: capacity, redundancy, config. Process: how we work. Tooling: what we use. Training: knowledge gap. Policy: rules. Detection: monitoring/alerting/runbooks.
Tied to root cause | Reference the specific root cause from the post-mortem RCA. Helps identify systemic vs one-off fixes.
Status | Open: not started. In Progress: being worked. Done: implemented. Verified: confirmed effective via test/audit/drill. Dropped: deliberately not pursuing (record rationale in Notes).
Verification | 30/60/90-day check after Done. Did the fix actually close the gap? Confirmed effective / Partially effective / Not effective.
Re-incident check | Has anything similar happened since this action was Done? If Yes, the action wasn't effective — re-open or replace.
Overdue | Due date column auto-highlights actions past due that aren't Done/Verified/Dropped.

## Lessons Learned
Lessons Learned
Captured throughout the project, finalized at close.
ID | Date | Category | Lesson / observation | Recommendation for next time | Owner to share / apply | Status

## Closeout
Project Closeout Report
Completed at project close.
Project name
Closeout date
Reported by
FINAL OUTCOMES
Objectives met (Y/N + summary) | For each charter objective: was it delivered?
Success criteria achieved | Per charter — score against each measurable criterion
Final scope vs original | What shipped vs what was originally planned
Final schedule vs original | Planned end vs actual end — explain variance
Final budget vs approved | Approved budget vs actual spend — explain variance
BENEFITS REALIZATION
Expected business value (from charter) | Restate what the project promised
Realized benefits to date | What's already been measured / achieved
Outstanding benefits | Benefits expected to materialize after closeout — and when
Benefit owner post-closeout | Who tracks realized benefits going forward
Measurement plan | How and when realized benefits will be verified
STAKEHOLDER FEEDBACK
Sponsor feedback | From sponsor
Customer / business feedback | From end users / business unit
Team feedback | From the project team
OPEN ITEMS AT CLOSE
Outstanding risks transferred | Risks that persist beyond the project — to whom transferred
Unfinished deliverables | If anything is incomplete — handoff plan
Operational handoff | Who owns the deliverables operationally
LESSONS & KNOWLEDGE TRANSFER
Top 3 wins to repeat | From Lessons Learned
Top 3 changes for next time | Biggest things to do differently
Knowledge base updates made | Where lessons were filed for reuse
ARCHIVE & DOCUMENTATION
Workbook archive location | Where this workbook is stored
Supporting documents archived | Charter, contracts, design docs, test results
Records retention period | How long these records must be retained
APPROVALS
Sponsor sign-off on closeout | Name, date
PMO sign-off on closeout | Name, date
Finance sign-off (budget close) | Name, date