## Slide 1
Project Atlas — Security Modernization
Program Status Report | Reporting Period: June 9–13, 2026
IN PROGRESS
Program Manager: Casey Morrison
OVERALL HEALTH
AT RISK
▼
SCOPE
ON TRACK
◆
SCHEDULE
AT RISK
◆
RESOURCES
AT RISK
▲
BUDGET
ON TRACK
◆
Trend vs prior period: ▲ improved ◆ steady ▼ declined
PORTFOLIO HEALTH
ZTNA · ON TRACK
MFA · AT RISK
PAM · ON TRACK
KEY MILESTONES
Program baseline · May 29
PAM recovery gate · Jul 22
Q4 go-live gate · Oct 12
EXECUTIVE SUMMARY
The program remains on track for the Q4 2026 delivery commitment. Two of three projects are executing to plan; MFA is trending yellow on schedule with recovery actions in flight. No change to scope, budget, or the decision calendar.
KEY ACHIEVEMENTS
Program integrated schedule baselined and approved by steering
Identity data readiness assessment completed across all sources
Executive risk acceptance framework ratified with sponsors
WHAT'S NEXT
Steering checkpoint on MFA schedule recovery (week of Jun 20)
Finalize cross-project cutover sequencing for Q4 go-live
Launch change readiness survey for wave 1 stakeholders
NEW DEPENDENCIES
status · need-by
RESOURCE
Integration engineer shared by IGA and MFA workstreams
Aug 1
◀ NEEDS
HR data cleansing gates identity testing
Jul 18
FEEDS ▶
SSO cutover date to service desk training
Sep 4
DECISION NEEDED
Approve executive escalation of the data sharing agreement to expedite legal sign-off
Decide by: Jul 10
NEW RISKS, ISSUES & BLOCKERS
Mitigation plans address risks; remediation plans address issues and blockers
TYPE | SEV | ITEM | MITIGATION / REMEDIATION PLAN | OWNER | TARGET
RISK | M | Vendor services capacity may tighten in Q4 | Mitigation: reserve Q4 vendor hours; cross-train two engineers | PgM | Jul 31
ISSUE | H | MFA vault provisioning delayed 3 weeks by change freeze | Remediation: change exception approved; recovery dates revised | MFA PM | Jul 24
BLOCKER | H | Data sharing agreement pending legal sign-off | Remediation: escalated to sponsor; legal review this week | Sponsor | Jul 10

## Slide 2
MFA Modernization — Project Atlas
Project Status Report | Reporting Period: June 9–13, 2026
IN PROGRESS
Project Manager: Casey Morrison
OVERALL HEALTH
AT RISK
▼
SCOPE
ON TRACK
◆
SCHEDULE
AT RISK
◆
RESOURCES
AT RISK
▲
BUDGET
ON TRACK
◆
Trend vs prior period: ▲ improved ◆ steady ▼ declined
KEY MILESTONES
Connector build · Jun 20
Integration testing · Jul 15
Cert campaign design · Aug 10
UAT complete · Sep 18
EXECUTIVE SUMMARY
MFA Wave 2 is at-risk on FIDO2 token supply; a buffer-stock draw (DC-028) holds the 6/27 cutover if ratified this week. All other milestones track to baseline, and UAT for the self-service portal passed at 96% first-run.
KEY ACHIEVEMENTS
All four source connectors built and promoted to test
Joiner-mover-leaver workflows approved by HR and IT security
Role mining pilot complete: 82% of access mapped to roles
WHAT'S NEXT
Begin end-to-end integration testing across connected sources
Kick off certification campaign design with audit and compliance
Draft wave 1 application onboarding runbook for operations
DEPENDENCIES
status · need-by
◀ NEEDS
HR data cleansing gates lifecycle testing
Jul 18
INTERNAL
Role model sign-off gates cert campaign build
Aug 1
FEEDS ▶
Provisioning feeds to PAM account discovery
Aug 15
DECISION NEEDED
None this period
NEW RISKS, ISSUES & BLOCKERS
Mitigation plans address risks; remediation plans address issues and blockers
TYPE | SEV | ITEM | MITIGATION / REMEDIATION PLAN | OWNER | TARGET
RISK | M | Remaining units may show lower role coverage | Mitigation: staged rollout with birthright-only fallback | Tech Lead | Aug 14
ISSUE | L | Test refresh removed connector configuration | Remediation: config restored; refresh freeze agreed | Tech Lead | Closed
BLOCKER | — | None reported this period | N/A | — | —

## Slide 3
How to Read This Report Template
Key, definitions, and color reference — so every project reports status the same way
REFERENCE
HEALTH · OVERALL, SCOPE, SCHEDULE, RESOURCES, BUDGET
ON TRACK
On plan. No leadership help needed
AT RISK
Off plan; credible recovery plan in flight
OFF TRACK
Objective in jeopardy. Leadership action required
TREND
▲ improved ◆ steady ▼ declined
vs prior reporting period
PROJECT STATUS
NOT STARTED
Pre-execution: planning and readiness underway
IN PROGRESS
Executing against the approved baseline
DELAYED
Behind baseline; recovery plan required
COMPLETE
Delivered and closed out
DEPENDENCY TAGS
each dependency also carries a health dot and a need-by date
◀ NEEDS
Upstream: waiting on another team or project
FEEDS ▶
Downstream: another team is waiting on us
RESOURCE
Shared person or team the work depends on
INTERNAL
A task inside the project blocks another task
RISK · ISSUE · BLOCKER
SEVERITY
one scale for risks, issues, and blockers
RISK
Might happen. Carries a mitigation plan to reduce likelihood or impact before it lands
ISSUE
Happening now. Carries a remediation plan with an owner and a target date
BLOCKER
Work is stopped until cleared. Remediate and escalate immediately
HIGH
Threatens go-live, the critical path, compliance, or scope. Requires executive attention and a decide-by date
MEDIUM
Impacts milestones or quality but recoverable with a plan. PM manages; leadership informed/involved in resolution if necessary
LOW
Minimal or contained impact. Team manages; tracked on the register and monitored
COLOR PALETTE (HEX)
PowerPoint: any color menu → More Colors → Custom → enter Hex
ACCENTS
Green 1E7E34
Amber B45309
Red B91C1C
Dark red 7C2D12
Teal 0F6B72
Blue 1D4ED8
Violet 7C3AED
Gray 4B5563
FILLS
On track E8F3EC
At risk/Delayed FFF2CC
Off track FBEAEA
In progress E2F0D9
Complete DEEBF7
Not started EEF0F2