## Document Control
Training & Awareness Plan — Document Control
| Program | [Program name]
| Artifact | Training & Awareness Plan
| Version | v1.0 — Final template for OCM team use
| Owner | Training Lead (or OCM Lead where no dedicated training role exists)
| Reviewers | OCM Lead; Program Manager; audience points of contact
| Approver | Program Sponsor
| Last revised | [date]
| Lock point | Detailed delivery schedule locked six weeks before each wave go-live; refreshed per wave and for reinforcement.
| Refresh cadence | Training Needs reassessed whenever the Change Impact Assessment is reassessed; completion tracking updated weekly during active delivery.
| System of record note | Enrollment and completion records live in the learning management system where one exists; this workbook owns the plan, schedule, and readiness rollup.
| Linked artifacts | Change Impact Assessment — Skills & Knowledge ratings and Behavior Change statements are the source of every training need
Communications Plan — training invitations, reminders, and completion nudges are scheduled in the plan's calendar, not sent ad hoc
Stakeholder Assessment — Sponsor Coalition Say / Attend / Sign actions include opening flagship sessions and reinforcing completion deadlines
Readiness Gates — completion thresholds on the Completion & Assessment tab are go / no-go criteria

## Instructions
Training & Awareness Plan — Instructions & Method
Purpose
This workbook operationalizes the training strategy: who is trained on what, when, by whom, in what format, with what assessment, and to what completion threshold before each readiness gate. It converts the Change Impact Assessment's Skills & Knowledge findings into a curriculum, a delivery schedule, and a completion rollup the gates can consume.
Derivation rule
Every training need derives from the Change Impact Assessment. A High Skills & Knowledge rating requires Proficiency-level training (formal, assessed, before go-live). Medium requires Working Knowledge (guided sessions or workshops). Low requires Awareness only (job aid or announcement — often satisfied by the Communications Plan alone, with no course needed). If a course exists with no impact-assessment row behind it, question the course; if a High rating exists with no course, that is a gate risk.
How the tabs connect
1. Training Needs — one row per change-audience pair with a Skills & Knowledge impact, carrying the learning objective and required depth. Pull the Behavior Change statement from the Impact Assessment; the learning objective is that statement rewritten as a capability.
2. Curriculum — the course catalog: one row per course or asset, with modality, duration, developer, and build status.
3. Delivery Schedule — courses mapped to audiences and waves with dates, trainers, and the stage gate each delivery must precede.
4. Completion & Assessment — required versus completed headcount per audience-course pair. Completion % calculates automatically; the threshold column is the readiness gate criterion.
5. Sustainment — reinforcement after go-live: refreshers, job aid upkeep, office hours wind-down, and new-hire onboarding integration so capability survives turnover.
6. Training Summary — automatic rollups for gate reviews and status reporting.
Coordination with the Communications Plan
Training communications ride the Communications Plan calendar: invitations land in the plan's phase arc ahead of each wave, reminders and completion nudges are scheduled entries, and sponsors reinforce deadlines through their Say actions. Awareness-depth needs are usually met by the plan's own communications — record them on Training Needs as satisfied by communications so the trace is explicit rather than missing.
Operating rhythm
Draft Training Needs as the Change Impact Assessment's ratings are finalized — needs derive from the Skills & Knowledge ratings and Behavior Change statements, so they firm up as the future state becomes known and are completed before the Design gate closes. Build curriculum during Build / Test / Validation, starting with Proficiency-depth courses, which need the longest runway for assessment development and delivery. Lock the delivery schedule six weeks before each wave go-live. Track completion weekly during active delivery and bring the Training Summary to every readiness gate review. After go-live, shift to the Sustainment tab and fold enduring content into new-hire onboarding.
Quality bar
Every High Skills & Knowledge rating in the impact assessment has a Proficiency-depth row here with an assessment method. Every completion threshold maps to a named readiness gate. Every course has an owner and a build status. Help Desk Teams train before the audiences they support, not alongside them.
Legend
White cell = enter data ¦ Grey cell = formula, do not edit ¦ Red / Amber / Green = attention / watch / healthy ¦ Italic row = worked example, replace with real data

## Reference Data
Reference Data — used by lookups and dropdowns (do not edit)
Audience ID | Audience Group (mirrors the Communications Plan)
AUD-01 | Executive Leadership
AUD-02 | People Leaders
AUD-03 | Frontline Staff
AUD-04 | General Workforce
AUD-05 | IT & Application Owners
AUD-06 | Help Desk Teams
AUD-07 | External Partners
Depth | Definition and impact-rating mapping
Proficiency | Formal training with assessment, completed before go-live. Required where Skills & Knowledge impact is High.
Working Knowledge | Guided sessions or workshops; practice included, light assessment. Required where impact is Medium.
Awareness | Job aid, knowledge article, or announcement. Sufficient where impact is Low; often satisfied by the Communications Plan.

## Training Needs
Training Needs — derived from the Change Impact Assessment; one row per change-audience pair with a skills impact
Need ID | Change ID | Audience ID | Audience Group | Skills & Knowledge Impact | Behavior Change (from Impact Assessment) | Learning Objective (capability statement) | Required Depth | Satisfied By | Priority
TN-01 | CH-01 | AUD-05 | IT & Application Owners | Medium | From validating logins app-by-app with local credentials → to validating role-based access through SSO test plans before each wave. | App owners can build, execute, and sign off a role-based SSO validation test plan for their application. | Working Knowledge | Course | High

## Curriculum
Curriculum — one row per course or asset; every course traces back to Need IDs
Course ID | Course / Asset Title | Description | Need IDs Covered | Modality | Duration | Developer / Owner | Build Status | Prerequisites | Review Sign-off
CRS-01 | SSO Validation Test-Plan Workshop | Hands-on workshop: building and executing a role-based validation test plan in the test tenant, ending with a signed practice sign-off. | TN-01 | Workshop | 90 min | Training Lead | In Build | Test-tenant access provisioned | OCM Lead + technical SME

## Delivery Schedule
Delivery Schedule — locked six weeks before each wave; every delivery precedes a named stage gate
Course ID | Audience ID | Audience Group | Wave / Phase | Delivery Window (start) | Delivery Window (end) | Trainer / Facilitator | Sessions Planned | Capacity per Session | Must Complete Before (Stage Gate) | Invitation via Communications Plan | Status
CRS-01 | AUD-05 | IT & Application Owners | Wave 1 | [YYYY-MM-DD] | [YYYY-MM-DD] | Training Lead + SSO SME | 4 | 15 | Build / Test / Validation | Action phase: invite 3 weeks out, reminder 1 week out | Scheduled

## Completion & Assessment
Completion & Assessment — track training completion against each gate's required threshold; when Threshold Met = Yes, this audience's training requirement is satisfied for its readiness gate
Course ID | Audience ID | Audience Group | Required Headcount | Completed | Completion % | Gate Threshold % | Threshold Met | Assessment Method | Pass Criteria | Stage Gate | Status
CRS-01 | AUD-05 | IT & Application Owners | 45 | 38 | 84.44% | 100% | No | Hands-on check: each app owner performs a practice validation during the workshop | App owner completes the practice validation correctly on their own, without instructor help | Build / Test / Validation | In Delivery

## Sustainment
Sustainment — reinforcement after go-live so capability survives turnover and drift
Item ID | Audience ID | Audience Group | Sustainment Activity | Trigger / Timing | Owner | New-Hire Onboarding Integration | Review Date | Status
SU-01 | AUD-05 | IT & Application Owners | Quarterly refresher on validation test-plan updates; job aid reviewed and reissued after each platform release. | Quarterly, and per platform release | Training Lead | Validation job aid added to new app-owner onboarding checklist; owned by IT onboarding coordinator. | [YYYY-MM-DD] | Planned

## Training Summary
Training Summary — automatic rollups for gate reviews and status reporting
Curriculum Build Status
| Not Started | 0
| In Build | 1
| In Review | 0
| Ready | 0
Delivery Status
| Planned | 0
| Scheduled | 1
| In Delivery | 0
| Complete | 0
| At Risk | 0
Gate Thresholds Met
| Yes | 0
| No | 1
Training Needs by Priority
| High | 1
| Medium | 0
| Low | 0
Counts include worked example rows until they are replaced with real data.